## Project Planner
Dissertation Project
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Programming the agent | 1 | 13 | na | na | na
get familiar with the coding environment | 1 | 2 | na | na | na
coding a random agent | 3 | 2 | na | na | na
experiment with random agent | 5 | 2 | na | na | na
record the result | 5 | 2 | na | na | na
Programming the agent with RL | 7 | 5 | na | na | na
debug the RL agent | 12 | 2 | na | na | na
Test the agent In Mini-map | 14 | 6 | na | na | na
MoveToBeacon | 14 | 1 | na | na | na
CollectMineralShards | 15 | 1 | na | na | na
CollectMineralsAndGas | 16 | 1 | na | na | na
DefeatRoaches | 17 | 1 | na | na | na
DefeatZerglingsAndBanelings | 18 | 1 | na | na | na
FindAndDefeatZerglings | 19 | 1 | na | na | na
Train the agent and record the result | 14 | 11 | na | na | na
Install necessary tools in super computer | 14 | 6 | na | na | na
run the agent in super computer | 20 | 5 | na | na | na
record the result | 20 | 5 | na | na | na
Evaluate the agent | 25 | 11 | na | na | na
Run the agent in testing mode | 25 | 1 | na | na | na
compare with the random agent | 25 | 1 | na | na | na
record the result | 25 | 1 | na | na | na
invite some volunteer to play with the agent | 26 | 8 | na | na | na
collect the result | 34 | 2 | na | na | na
Final dissertation | 1 | 59 | na | na | na
Write the report (experiment, result, discussion, etc.) | 36 | 14 | na | na | na
shoot some footage | 1 | 35 | na | na | na
Write PPT to demostrate the project, or create video | 36 | 14 | na | na | na
practice demostration | 50 | 10 | na | na | na

## Sheet1
Dissertation Project
Select a period to highlight at right. A legend describing the charting follows. |  |  | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | PERIODS
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Programming the agent | 1 | 13
get familiar with the coding environment | 1 | 2
coding a random agent | 3 | 2
experiment with random agent | 5 | 2
record the result | 5 | 2
Programming the agent with RL | 7 | 5
debug the RL agent | 12 | 2
Test the agent In Mini-map | 14 | 6
MoveToBeacon | 14 | 1
CollectMineralShards | 15 | 1
CollectMineralsAndGas | 16 | 1
DefeatRoaches | 17 | 1
DefeatZerglingsAndBanelings | 18 | 1
FindAndDefeatZerglings | 19 | 1
Train the agent and record the result | 14 | 11
Install necessary tools in super computer | 14 | 6
run the agent in super computer | 20 | 5
record the result | 20 | 5
Evaluate the agent | 25 | 11
Run the agent in testing mode | 25 | 1
compare with the random agent | 25 | 1
record the result | 25 | 1
invite some volunteer to play with the agent | 26 | 8
collect the result | 34 | 2
Final dissertation | 1 | 59
Write the report (experiment, result, discussion, etc.) | 36 | 14
shoot some footage | 1 | 35
Write PPT to demostrate the project, or create video | 36 | 14
practice demostration | 50 | 10